## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Intoduction to project (cyber risk assessment system) | MUST HAVE | No Dependency | Reddimalli Ruthika | 3- Completed
S1 | S1 | US-001 | Workflow creation and project planning | MUST HAVE | Lucid Chart | Reddimalli Ruthika | 3- Completed
S2 | S2 | US-001 | Requirements analysis and use case preparation | MUST HAVE | No Dependency | Reddimalli Ruthika | 3- Completed
S2 | S2 | US-001 | Design system architecture and modules | SHOULD HAVE | Research Papers | Reddimalli Ruthika | 3- Completed
S3 | S3 | US-001 | Implement Nmap scanning module | MUST HAVE | Nmap tool | Reddimalli Ruthika | 3- Completed
S4 | S4 | US-001 | Develop database (SQLite) for storing scan results | MUST HAVE | SQLite | Reddimalli Ruthika | 3- Completed
S5 | S5 | US-001 | Develop Streamlit dashboard UI | MUST HAVE | Streamlit | Reddimalli Ruthika | 3- Completed
S6 | S6 | US-001 | Implement risk scoring and severity calculation | SHOULD HAVE | Python Logic | Reddimalli Ruthika | 3- Completed
S7 | S7 | US-001 | Integrate Virustotal API for threat intelligence | SHOULD HAVE | Virustotal API | Reddimalli Ruthika | 3- Completed
S8 | S8 | US-001 | Implement report generation and email alert system | MUST HAVE | SMTP, FPDF | Reddimalli Ruthika | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 22 | 12 | 11 | 9 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Project introduction and setup | 9-Feb--26 | 10-Feb--26 | Reddimalli Ruthika | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | workflow creation | 10-Feb--26 | 12-Feb--26 | Reddimalli Ruthika | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Requirements analysis | 12-Feb--26 | 15-Feb--26 | Reddimalli Ruthika | Design | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Sysytem design | 15-Feb--26 | 18-Feb--26 | Reddimalli Ruthika | Design | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Nmap scanning implemantation | 18-Feb--26 | 22-Feb--26 | Reddimalli Ruthika | Coding | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Database integration | 22-Feb--26 | 25-Feb--26 | Reddimalli Ruthika | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Streamlit dashboard creation | 25-Feb--26 | 28-Feb--26 | Reddimalli Ruthika | Build | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Risk scoring logic | 2026-03-01 | 2026-03-06 | Reddimalli Ruthika | Coding | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | VirusTotal API integration | 2026-03-06 | 2026-03-18 | Reddimalli Ruthika | Integration Test | 3- Completed | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Report generation & email alerts | 2026-03-18 | 2026-03-27 | Reddimalli Ruthika | Integration Test | 3- Completed | 8 | 3 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity in project requirements | Discussed with mentor and clarrified requirements
Sprint 1 | Day 5 | Confusion in workflow and architecture design | conducted brainstorming and finalized workflow
Sprint 2 | Day 10 | Difficulty in identifying use cases | researchedd online resources and documentation
Sprint 2 | Day 14 | Issue in designing system modules | reviewed design and improved structure
Sprint 2 | Day 18 | Errors in Nmap scanning implementation | debugged code and referred documentation
Sprint 3 | Day 22 | Database connection issues | fixed SQLite integration errors
Sprint 4 | Day 28 | UI alignment issues in Streamlit dashboard | adjusted layout and improved UI design
Sprint 4 | Day 32 | Difficulty in risk score calculation logic | Optimized formula and tested outputs
Sprint 5 | Day 38 | API integration errors (VirusTotal) | debugged API calls and handled responses
Sprint 5 | Day 45 | Email alert not sending properly | fixed SMTP configuration

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-09 | 2026-02-16 | Reddimalli Ruthika | documenting requirements clearly | unclear planning | Referring documentation and learning resources | Scheduled review sessions with mentor to clarify project goals
2 | Sprint 2 | 2026-02-17 | 2026-02-24 | Reddimalli Ruthika | UI testing early | last-minute UI fixes | Participating in mentor discussions | Completed Python module implementation independently
3 | Sprint 3 | 2026-02-25 | 2026-03-05 | Reddimalli Ruthika | breaking logic into steps | overcomplicating logic | Maintaining focus on coding | Resolved SQL issues
4 | sprint 4 | 2026-03-06 | 2026-03-15 | Reddimalli Ruthika | proper API testing | ignoring API errors | Asking for help when stuck | Fixed errors through self-debugging and testing
5 | sprint 5 | 2026-03-16 | 27/32026 | Reddimalli Ruthika | testing email configs early | incorrect configurations | Debugging and testing code regularly | Used online resources to improve implementation and fix bugs